## Sheet1
TASK | Team | start date | days to complete
Requirement Specification | Amarendhar reddy, Vaishnavi Choppalli | 2022-01-31 | 3
Scheduling | Subbarao | 2022-02-03 | 2
Development Plan | T KavyaKeerthi | 2022-02-05 | 2
Resource Allocation | Aparna Mirapakayala, Narisamharoa Gurram | 2022-02-07 | 3
Risk Management Plan | Neha Chowdary Puvvada, Kalyani Virivinti | 2022-02-10 | 12